## Sheet1
Tasks | # of Hours | Deadline
Search page - get user input and send to server | 20 | 2015-12-23
Send search data to backend | 10 | 2015-12-30
Results page - read from server and output data | 10 | 2015-12-30
Upload picture and description of tourist spot | 5 | 2016-01-06
Send new picture and description to backend | 5 | 2016-01-06
Page with new item | 5 | 2016-01-06